## Sheet1
Phonebook
Project Leader- Sanket Vijaykumar Chougala | Chougala
Timeline For Project
TASK | ASSIGNED TO | PROGRESS | START | END | Timeline and hours
Phase 1 Title
Requirements | Sanket Chougala | 100% | 2022-03-15 | 2022-03-18 |  | 5hr
Architecture | Sanket Chougala | 100% | 2022-03-18 | 2022-03-20 |  |  | 6hr
Implementation | Sanket Chougala | 100% | 2022-03-21 | 2022-03-25 |  |  |  | 8hr
TestPlanAndoutput | Sanket Chougala | 100% | 2022-03-26 | 2022-03-27 |  | 4hr
Report, Images | Sanket Chougala | 100% | 2022-03-28 | 2022-03-30 | 2hr